## Sheet1
Feature | Initial Estimate | Week 1 | Week 2 | Week 3 | Week 4
Sprint 1 | 15 | 2 | 0 | 4 | 3
Settting | Start | Week 1 | Week 2 | Week 3 | Week 4
Planned Hours |  | 1.25 | 1.25 | 1.25 | 1.25
Actual Hours |  | 2 | 0 | 4 | 3
Remaining Effort | 15 | 13 | 13 | 9 | 6
Ideal Burndown | 15 | 13.75 | 12.5 | 11.25 | 10